## Data
id | parent_id | phase | task | milestone | start | end | completion | dependencies | assignee | status
100 |  |  | Projeto Exemplo | FALSE |  |  | 0
101 | 100 |  | Initiation | FALSE |  |  | 0
102 | 100 |  | Design | FALSE |  |  | 0
103 | 100 |  | Implementation | FALSE |  |  | 0
104 | 100 |  | Testing | FALSE |  |  | 0
2 | 101 |  | Requirements gathering | FALSE | 25/09/2025 | 27/09/2025 | 50 |  |  | High
3 | 101 |  | Requirements gathering 2 | FALSE | 27/09/2025 | 29/09/2025 | 55 | 2 | Day Bacci | Medium
4 | 101 |  | Stakeholder workshop excl. Execs | FALSE | 29/09/2025 | 01/10/2025 | 75 | 3 |  | Medium
5 | 101 |  | Story boarding | FALSE | 29/09/2025 | 07/10/2025 | 80 | 3 |  | Low
6 | 101 |  | Initiation complete | TRUE | 07/10/2025 | 07/10/2025 | 0 | 4,5
8 | 102 |  | E2E data solution design | FALSE | 01/10/2025 | 03/10/2025 | 100 | 6 |  | High
9 | 102 |  | Wireframes | FALSE | 03/10/2025 | 08/10/2025 | 80 | 8 |  | Medium
10 | 102 |  | Prototyping | FALSE | 07/10/2025 | 17/10/2025 | 40 | 9 |  | Low
11 | 102 |  | Design complete | TRUE | 17/10/2025 | 17/10/2025 | 0 | 10
13 | 103 |  | ETL | FALSE | 03/10/2025 | 14/10/2025 | 15 | 6 |  | Very High
14 | 103 |  | Data modelling | FALSE | 07/10/2025 | 14/10/2025 | 40 | 13 |  | High
15 | 103 |  | Measures & KPIs | FALSE | 07/10/2025 | 10/10/2025 | 50 | 14 |  | Medium
16 | 103 |  | Visuals | FALSE | 10/10/2025 | 20/10/2025 | 25 | 15 |  | Medium
17 | 103 |  | Implementation complete | TRUE | 24/10/2025 | 24/10/2025 | 0 | 16
18 | 104 |  | UAT | FALSE | 20/10/2025 | 29/10/2025 | 0 | 16 |  | High
19 | 104 |  | Bug fixes | FALSE | 24/10/2025 | 30/10/2025 | 0 | 17 |  | Medium
20 | 104 |  | Go-Live | TRUE | 31/10/2025 | 31/10/2025 | 0 | 18,19 |  | Very High

## Instructions
How to fill this template — Interactive Gantt Chart
Fill the 'Data' sheet and import this file into gantt.html via the Import button.
Column | Type | Required | Description and rules
id | Integer | Yes | Unique identifier. Use sequential numbers. Referenced by 'dependencies' and 'parent_id'.
parent_id | Integer | No | ID of parent task. Empty = root node. Defines hierarchy: Project > Workstream > Phase > Sub-phase > Task. Unlimited depth. Cycles are detected and blocked.
phase | Text | No | [Legacy] If parent_id is empty but phase is filled, the app auto-creates a phase summary. Recommended: leave empty and use parent_id explicitly.
task | Text | Yes | Description shown on the bar. Ideally up to 60 characters.
milestone | TRUE/FALSE | No | TRUE = diamond. FALSE = bar. For milestones, start = end.
start | Date DD/MM/YYYY | Yes | Start date. Accepts Excel native date format.
end | Date DD/MM/YYYY | Yes | End date. Must be ≥ start.
completion | Integer 0-100 | No | Percent of deliverable produced. See '% Completion' sheet.
dependencies | Text | No | Predecessor IDs comma-separated. Ex.: '2,3'.
assignee | Text | No | Owner (free text). Shown in tooltip.
status | List | No | Very High / High / Medium / Low / (empty). Sets bar color.
General rules and tips
1. Don't leave blank rows between tasks — importer stops at the first empty.
2. IDs don't need to be sequential without gaps, but must be unique and stable.
3. Dates: accepts both Excel date and DD/MM/YYYY text.
4. To create a new phase, just type a new name in 'phase'.
5. Milestones represent points in time — always start = end.
6. Circular dependencies produce inconsistent arrows. Avoid them.
7. Empty status = neutral gray (useful for generic milestones).
8. Save, open gantt.html, click Import, choose 'Replace all'.
9. You can mix this Excel with inline editing afterwards.
10. For Git collaboration, export as CSV.

## Status Glossary
Status (priority) — visual reference
Value | Color | When to use
Very High |  | Critical. Critical path or absolute blocker.
High |  | High priority. Delays have significant impact.
Medium |  | Default for most tasks.
Low |  | Low priority. Can be rescheduled.
(empty) |  | No priority defined.

## % Completion
'completion' field — detailed logic
Task completion percentage, range 0 to 100. This sheet explains how the value is interpreted by the Gantt, how phases aggregate, and what criteria to use when filling it.
1. How the app renders it visually
The task bar is drawn in two overlapping layers: • A background bar (light color, 30% opacity) representing the total duration. • A progress bar (solid color) occupying exactly 'completion'% of the background width. So: completion=0 → only light background; completion=50 → half filled; completion=100 → fully filled.
Visual example (bar width = % filled):
0%
25%
50%
75%
100%
2. Milestones (milestone=TRUE) ignore this field
Milestones are points in time, not periods — so the concept of 'partial completion' doesn't apply. The app renders milestones as filled diamonds, regardless of the 'completion' value. Convention: leave completion=0 on milestones.
3. Who fills and who the app computes
There are 3 row types. Golden rule: you fill LEAVES, the app computes SUMMARIES.
Row type |  |  | Who decides the %? |  | Example in default project
Leaf (no children) |  |  | You fill it manually (0-100) |  | Wireframes = 80
Summary (has children) |  |  | App computes. DON'T fill — it'll be overwritten. |  | Design = avg of leaves
Milestone (milestone=TRUE) |  |  | Leave 0. App ignores in aggregation. |  | Go-Live
4. Recursive formula (works at any depth)
For each summary node (any level: project, workstream, phase, sub-phase), the app: 1. Walks the ENTIRE descendant tree collecting LEAVES 2. Discards milestones (milestone=TRUE) 3. Computes SIMPLE AVERAGE of those leaves' % Pseudocode: function compute_pct(node): if node has NO children: ← it's a leaf return node.completion else: leaves = all descendant leaves (recursion) valid = leaves where milestone == FALSE if valid is empty: return 0 return SUM(valid[i].completion) / COUNT(valid) Mathematical notation: %_summary = Σ(%_non_milestone_leaves) / N_non_milestone_leaves
5. Full worked example — 3 levels, 13 leaves
Consider the default dataset (Sample Project). See the bottom-up calculation — each row shows level, type, applied formula and result:
Node |  |  | Level | Type | Calculation | Result
Requirements gathering |  |  | 2 | leaf | — | 50
Requirements gathering 2 |  |  | 2 | leaf | — | 55
Stakeholder workshop |  |  | 2 | leaf | — | 75
Story boarding |  |  | 2 | leaf | — | 80
Initiation complete |  |  | 2 | milestone | (ignored) | —
▸ Initiation |  |  | 1 | summary | (50+55+75+80)/4 | 65%
E2E data solution design |  |  | 2 | leaf | — | 100
Wireframes |  |  | 2 | leaf | — | 80
Prototyping |  |  | 2 | leaf | — | 40
Design complete |  |  | 2 | milestone | (ignored) | —
▸ Design |  |  | 1 | summary | (100+80+40)/3 | 73%
ETL |  |  | 2 | leaf | — | 15
Data modelling |  |  | 2 | leaf | — | 40
Measures & KPIs |  |  | 2 | leaf | — | 50
Visuals |  |  | 2 | leaf | — | 25
Implementation complete |  |  | 2 | milestone | (ignored) | —
▸ Implementation |  |  | 1 | summary | (15+40+50+25)/4 | 33%
UAT |  |  | 2 | leaf | — | 0
Bug fixes |  |  | 2 | leaf | — | 0
Go-Live |  |  | 2 | milestone | (ignored) | —
▸ Testing |  |  | 1 | summary | (0+0)/2 | 0%
■ SAMPLE PROJECT |  |  | 0 | root | sum of 13 leaves / 13 = 610/13 | 47%
Root verification: 50+55+75+80 + 100+80+40 + 15+40+50+25 + 0+0 = 610. 610 ÷ 13 = 46.92% → rounded to 47%.
6. CAUTION: average of LEAVES, not of phases
The root's % is NOT the average of phases — it's the average of leaves DIRECTLY. Phases with different task counts weigh differently between the two methods:
Calculation method |  |  | Formula |  | Result
Average of 4 phases (WRONG) |  |  | (65 + 73 + 33 + 0) / 4 |  | 43%
Average of 13 leaves (CORRECT) |  |  | 610 / 13 |  | 47%
The difference exists because Testing (only 2 leaves, both 0%) pulls the result down LESS when we look leaf-by-leaf. The app uses leaf average — deliberate choice. For weighted average by duration or effort, compute externally (the model has no weight column).
4. Suggested criteria (rubric)
Use the rubric below for consistency. Work in multiples of 25 — finer precision rarely reflects observable reality.
% | Meaning | When to use
0 | Not started | Task has not begun.
25 | Started | Work began. Partial deliverable exists.
50 | Halfway | About half of the effort spent.
75 | Almost done | Reviewed at least once. Final tweaks.
100 | Completed | Deliverable accepted by owner.
5. Common gotchas
! Don't use temporal percentage (days elapsed / total duration).
That calculation says nothing about actual deliverable progress.
! Don't fill 'completion' on the phase row.
It's auto-derived from child tasks.
! Don't use fractional values (37.5%).
The app accepts integers only.
! 100% ≠ 'client-approved'.
Formal approval is usually a separate milestone.
! Be careful flipping a task to milestone with completion > 0.
The value will be ignored; zero it out manually for hygiene.
! 100% with 'end' in the future is suspicious.
Update 'end' to the actual completion date.
6. One-line summary
'completion' is PERCENT OF DELIVERABLE produced (not time elapsed), filled by the task team in multiples of 25, ignored on milestones, aggregated by simple average on the phase row.